## Sprint 1 Backlog
User story | Story points associated to a US | Issue # | Associated Tasks | Priority | Risk (High, Medium, Low) | Responsible | Due Sprint/Date
SPRINT #1
#19 As a user, the I want to see a landing page with a navigation bar, so that I can easily navigate the application. | 2 | #29 | 1. Design frontend UI for a homepage including the navigation bar, login and register buttons. | HIGH | Low: layout/styling | Brian | 1
|  | #28 | 2. Build a navigation component that displays links based on user authentication status. | HIGH | Medium:Depends on correct session/auth state | Brian | 1
#2 As a user, I want to register for an account, so that I can start saving my dietary preferences and allergies to my profile. | 5 | #32 | 3. Configure the PostgreSQL database connection settings and export the connection instance. | HIGH | Medium: debugging can take time. | Juan | 1
|  | #33 | 4. Run raw SQL queries to initialize the database tables (`users`). | HIGH | Medium | Juan | 1
|  | #20 | 5. Implement database access methods for user data, including hashing passwords and finding users by email (to avoid duplicate emails). | HIGH | Medium | Elias | 1
|  |  | 6. Define API endpoint for user registration under `/api/auth`. | MED | Low: Straightforward routing | Abdullah | 1
|  |  | 7. Implement backend logic for user registration verification. | MED | Medium: possible edge cases | Abdullah | 1
|  | #25 | 8. Handle axios calls for register, and manage user session storage. | LOW | Medium: handling API errors consistently can be tricky | Dipita | 1
|  | #24 | 9. Design the registration page UI, including the registration form with validation and error handling. | LOW | Medium: Form validation + UX states can take multiple tries | Dipita | 1
#3 As a user, I want to login to my account, so that I can access and manage my profile. | 3 | #21 | 10. Implement database access methods for user data, including finding users by email and verifying password. | HIGH | Medium: small mistakes cause login failures | Elias | 1
|  |  | 11. Define API endpoint for user login under `/api/auth` | MED | Low: Straightforward routing | Abdullah | 1
|  |  | 12. Implement backend logic for user login verification. | MED | Medium: Common source of bugs | Abdullah | 1
|  | #27 | 13. Handle axios calls for login, and manage user session storage. | LOW | Medium: similar risks to registration | Dipita | 1
|  | #26 | 14. Design the login page UI, including the login form with validation and error handling. | LOW | Medium | Dipita | 1
#4 As a user, I want to view and update my profile, so that the application can provide me with meal recommendations tailored to my dietary needs and allergies. | 8 | #34 | 15. Run raw SQL queries to initialize the database tables (`user_profiles`). | HIGH | Medium: table creation order can cause SQL errors | Juan | 1
|  | #23 | 16. Implement database access methods for user profiles, including managing dietary preferences and allergies. | HIGH | Medium: update logic and validation can be a source of bugs | Elias | 1
|  | #35 | 17. Define protected API endpoints for user profile management under `/api/profile`. | MED | High: frequent failure issues | Juan | 1
|  | #22 | 18. Implement backend logic to fetch and update user-specific profile data based on the authenticated user. | MED | High: possibility of leaking or overwriting data | Elias | 1
|  | #30 | 19. Handle axios calls for profile retrieval and update, and manage user profile data. | LOW | Medium: keeping UI in sync with backend | Brian | 1
|  | #31 | 20. Design the user profile dashboard to view and manage dietary preferences and allergies. | LOW | Medium | Brian | 1

## Sprint 2 Backlog
User story | Story points associated to a US | Issue # | Associated Tasks | Priority | Risk (High, Medium, Low) | Responsible | Due Sprint/Date | Dependencies (#Issue)
SPRINT #2
#47 As a user, I want to create recipes, so that the application saves them. | 5 | #51 | Run raw SQL queries to initialize the database tables "recipes" | HIGH | HIGH - schema erros possible | Seb | Feb 18th
|  | #53 | Implement database access method 'create' for recipe creation. | HIGH | HIGH - DB logic complexity | Elias | Feb 19th | #51
|  | #58 | Define protected API endpoint for recipe creation under POST 'api/recipes' | MED | MED | Seb | Feb 21st | #53
|  | #62 | Implement backend logic to create recipe with provided attributes. | MED | MED | Abdullah | Feb 22nd | #58
|  | #73 | Handle axios calls to handle the creation of the recipe. | LOW | LOW - simple http req | Brian | Feb 23rd | #62
|  | #74 | Design the 'create' button on the recipes page and the corresponding form prompting for attributes. | LOW | LOW - frontend UI | Brian | Feb 23rd | #62
#48 As a user, I want to search for available recipes using filters, so that I can view them and their attributes. | 8 | #54 | Implement database access method 'findAll' for recipes retrieval. | HIGH | HIGH - dynamic query complex | Elias | Feb 19th
|  | #59 | Define protected API endpoint for recipe deletion under GET 'api/recipes'. | MED | MED - query parameter | Seb | Feb 21st | #54
|  | #63 | Implement backend logic to retrieve recipes using the filters set by user. | MED | HIGH - private-public recipes | Abdullah | Feb 22nd | #59
|  | #75 | Handle axios calls to handle the retrieval of requested recipes using filters. | LOW | LOW | Brian | Feb 23rd | #63
|  | #76 | Design search entries and filter entries on the recipes page. | LOW | LOW | Brian | Feb 23rd | #63
|  | #77 | Design recipes page to filter and display the requested recipes as a result of inputing search and filter entries. | LOW | LOW | Dipita | Feb 24th | #75, #76
#49 As a user, I want to edit recipes, so that the recipes in my account show updated information. | 3 | #55 | Implement database access method 'update' for recipe info update. | HIGH | HIGH - Complex query handling multiple fields, potential data integrity issues | Elias | Feb 19th
|  | #60 | Define protected API endpoint for recipe update under PUT 'api/recipes' | MED | MED - Route depends on authentication middleware and controller being correctly implemented | Seb | Feb 21st | #55
|  | #64 | Implement backend logic to update recipe with provided attributes. | MED | HIGH - Requires input validation | Abdullah | Feb 22nd | #60
|  | #78 | Handle axios calls to handle the update of the recipe. | LOW | LOW - Standard HTTP PUT reques | Dipita | Feb 24th | #64
|  | #79 | Design the 'edit' button on each recipe displayed and the corresponding form prompting for new attributes. | LOW | LOW - Reuses existing form component patterns | Dipita | Feb 24th | #64
#50 As a user, I want to delete recipes, so that they are removed from my account. | 3 | #56 | Implement database access method 'delete' for recipe deletion. | HIGH | HIGH - Permanent data removal requires careful handling | Elias | Feb 19th
|  | #61 | Define protected API endpoint for recipe deletion under DELETE 'api/recipes' | MED | MED - must ensure proper authentication to prevent unauthorized deletions | Seb | Feb 21st | #56
|  | #65 | Implement backend logic to delete selected recipe. | MED | HIGH - Must verify ownership before deletion, handle cases where recipe doesn't exist | Abdullah | Feb 22nd | #61
|  | #80 | Handle axios calls to handle the removal of the recipe. | LOW | LOW - Standard HTTP DELETE request | Dipita | Feb 24th | #65
|  | #81 | Design the 'delete' button on each recipe displayed. | LOW | LOW | Dipita | Feb 24th | #65